Proposal: Formalize the CDI Function

HealthProMed  ·  Coding & CDI  ·  Reporting-line change - no new headcount ask

The ask: Recognize Coding & CDI as a distinct function reporting outside of Billing (dotted line to Billing, solid line to Compliance / CMO / CFO). No new hires, no new budget - a structural change to protect audit independence.

1. Current state (3 months in)

Hired as a coder in the Billing department with responsibility for CPT II codes. In practice, the role has expanded into Clinical Documentation Improvement (CDI): a formal audit program, a scoring workbook, provider scorecards, and a completed Q3 quarterly rollup across 13 providers.

This CDI work is currently performed inside Billing, but CDI and Billing are distinct functions with different loyalties. Billing exists to move claims through the pipeline; CDI exists to slow claims down when documentation doesn't support them.

2. Why the reporting line matters

| Concern under current structure | What separation solves |
| --- | --- |
| Billing supervisor can override CDI queries or holds to keep the pipeline moving. | Audit findings and queries can be raised independently, without pipeline pressure. |
| External audits (RADV, OIG) view CDI-under-Billing as a structural conflict of interest. | OIG Compliance Program element #4 (internal auditing) is better satisfied with an independent function. |
| Single point of failure - the function only exists as long as one person performs it. | Formalization creates institutional memory, defined SOPs, and a path to scale. |
| CDI staff time gets absorbed into billing overflow work under pressure. | Protected time to run audits, education, and HCC recapture - the highest-ROI activities. |

3. Three reporting structure options

| Model | CDI reports to | Pros | Cons |
| --- | --- | --- | --- |
| A · Independent CDI | Compliance / CMO / Quality | Best independence · matches OIG guidance | Requires a mature Compliance function to absorb it |
| B · Revenue Integrity umbrella | CFO / VP Revenue Cycle | CDI sits at RCM level alongside (not under) Billing | Still lives with money-focused leadership |
| C · Dotted-line matrix (RECOMMENDED) | Solid: Compliance/CMO · Dotted: Billing | Independence + operational alignment with Billing | Requires clear communication of the matrix |

4. What we are NOT asking for (yet)

A second hire - deferred to month 6 with a formal business case backed by ROI data

New software or enterprise CDI platform - the current audit workbook is functional and free

A separate physical office, dedicated staff, or budget increase

Title inflation - starting with 'Coding & CDI Lead' is appropriate for year 1

5. Immediate asks (day one)

Formal role change from 'Coder in Billing' to 'Coding & CDI Lead' with a written scope of responsibilities

Reporting-line change per Model C (dotted-line to Billing, solid to Compliance / CMO / CFO)

Executive sponsor named (CMO, CFO, or VP Compliance) with a monthly 30-minute check-in on the calendar

Leadership endorsement to make monthly audits a mandatory participation for all providers

Permission to prepare a Certified Risk Adjustment Coder (CRC) hire business case at the 6-month checkpoint

6. 12-month milestones

| Milestone | Timing | Deliverable |
| --- | --- | --- |
| Function formalized | Month 3-4 | Written scope · reporting-line documented · sponsor named |
| Q4 audit cycle + corrective plans | Month 4-6 | 10 charts × top providers · corrective plans opened for <80% band |
| 6-month review + hire case | Month 6 | 6-month report · CRC hire business case presented |
| Q1 next-year audit cycle | Month 7-9 | Retest scores on corrective providers · systemic root cause investigation |
| Annual report + year-2 plan | Month 12 | Full-year report · year-2 roadmap · headcount ask |

7. Evidence supporting this ask

| Metric | Result |
| --- | --- |
| Providers audited this quarter | 13 |
| Charts audited this quarter | 130 |
| Program-wide average compliance % | 76.4% |
| Providers reaching Meets Expectations | 0 of 13 |
| Providers needing Corrective Education | 10 of 13 |
| Tools built (at zero software cost) | Audit workbook · KPI Tracker · HCC Recapture Tracker · Standard Report Template |
| Documentation produced | Program Overview · Auditor Guide · Coder Guide · Criteria Brief · Timing Calendar · Work Plan |

8. Risks and mitigation

| Risk | Mitigation |
| --- | --- |
| Billing supervisor feels displaced | Frame as function expansion · continue CPT II support to Billing · make Billing look good in the report |
| Leadership sees this as empire-building | No headcount ask · no new budget · role is already being performed - this is formal recognition |
| Providers push back on audits | Q3 findings already establish need · pitch audits as denial prevention and RADV protection |
| Single-point-of-failure risk | Every process documented · 6-month hire case addresses continuity directly |

Bottom line: The CDI function already exists at HealthProMed - it just does not have an org chart. This proposal formalizes what is already being delivered, protects the organization from compliance exposure, and costs nothing at signature.

Prepared by Eric Galan, CPC · CRC · Coding & CDI Lead  ·  Present alongside Q3 2026 Provider Audit Report