Coding & CDI Department — Startup Workflow

Sequenced step-by-step launch playbook · solo track · from Day 1 to Day 90

| Who this is for | The one person launching the Coding & CDI department |
| --- | --- |
| Time frame | First 90 days from launch |
| Outcome | Fully operational documentation-audit function + first quarterly leadership report |
| Prerequisites | Audit workbook, work plan, and support docs already prepared |

The launch flow at a glance

Five phases, ~90 days total. Each phase produces an artifact that unlocks the next one.

| Phase | Days | Focus | Artifact produced |
| --- | --- | --- | --- |
| 1 · Foundation | 1–7 | Get the sponsor, scope, and tools ready · pull HCC lists. | Signed scope agreement · payer HCC lists · tools in place. |
| 2 · First audit + HCC | 8–21 | Pick 3 providers · audit charts AND log HCC recaptures in the same pass. | Baseline compliance scores · first scorecards · first HCC recaptures. |
| 3 · Rhythm | 22–45 | Turn the first cycle into a repeatable process · first education tip. | Monthly SOP · Provider Education Tip #1. |
| 4 · Add HEDIS + expand | 46–75 | Layer HEDIS/CPT II gap review · consider adding a 4th–5th provider. | HEDIS gap list · expanded provider rotation. |
| 5 · Present to leadership | 76–90 | Quarterly report + build the case for month 6. | Q1 report · month-6 milestone plan. |

Phase 1 · Foundation  (days 1–7)

Get the department on paper before doing any actual audit work. This week is about alignment, not activity.

| 1 | Meet with your executive sponsor (CFO or Revenue Integrity lead). Confirm the department exists, its scope, and its reporting line. Output: One-page scope agreement signed by sponsor. Notes: Bring the Coding_CDI_Year1_Work_Plan for reference. |
| --- | --- |

| 2 | Confirm the provider list you will audit. Get the medical director's endorsement so audits are seen as mandatory, not optional. Output: List of 3 providers to start with · medical director email confirming. Notes: Start with the top 3 providers by MA / HCC volume. |
| --- | --- |

| 3 | Set up your workspace: shared drive folder for the workbook, KPI Tracker, HCC Recapture Tracker, and support docs. Turn on AutoSave if using SharePoint/OneDrive. Output: Folder structure · file access confirmed · AutoSave on. Notes: Suggested folders: /Audits, /HCC, /KPI, /Reference, /Reports. |
| --- | --- |

| 4 | Request access to payer portals and pull the prior-year HCC list for the MA/risk-adjusted patients of your first 3 providers. Print or export. Output: Prior-year HCC list per patient · ready alongside the audit workbook. Notes: You need this BEFORE Phase 2 so you can recapture HCCs in the same pass as the audit. |
| --- | --- |

| 5 | Book your recurring calendar events: monthly audit block (days 5-15), monthly leadership check-in (day 25), quarterly report slot (end of Q1/Q2/Q3/Q4). Output: Calendar invites sent and accepted. Notes: Recurring blocks protect your time · without them the work never happens. |
| --- | --- |

Phase 2 · First audit cycle + HCC recapture  (days 8–21)

Run the tool for real — and capture HCCs at the same time. Since you're already reading every chart end-to-end for the documentation audit, layer the HCC check into the same pass. One read of the chart, two workflows completed. Don't do them as separate cycles.

| 6 | Pull 10 charts per provider from the prior-month encounters (30 charts total for 3 providers). Output: Chart list logged on the Chart Sample Log tab (or in your Audit Log notes). Notes: Follow the 3 Diabetes · 2 CKD · 2 AWV · 2 High-RAF · 1 Random mix. |
| --- | --- |

| 7 | Open the audit workbook AND the HCC Recapture Tracker side by side. Also open the patient's prior-year HCC list (from Phase 1) for MA patients. Output: Both workbooks open · HCC list visible while auditing. Notes: This is the key setup that lets you audit + recapture in one pass. |
| --- | --- |

| 8 | For each chart: audit the 16 documentation elements on the Claim tab AND log any HCC finding on the HCC Recapture Tracker at the same time. Categorize each HCC as Prior-Year (recaptured or missed), Suspect, or New. Output: 30 completed Claim tabs · HCC Log rows for every HCC found or missed on those charts. Notes: One chart read = one audit row + one or more HCC log rows. Save the second pass through the chart later in the month for cases that need a query response. |
| --- | --- |

| 9 | Review the Provider Metrics tab for compliance % AND the HCC Recapture Tracker's Monthly Summary for recapture rate + RAF impact. Output: 3 provider scorecards with BOTH baseline compliance data and HCC recapture data. Notes: Two data points per provider from day one · double the story for leadership. |
| --- | --- |

| 10 | Draft a one-page scorecard email for each provider: their compliance %, top 2 documentation deficiencies, HCCs recaptured, HCCs missed with suggested capture language, one specific documentation tip. Output: 3 scorecard emails ready to send · integrated documentation + HCC feedback. Notes: Positive tone. HCC feedback is high-value to providers because it's tied to revenue. |
| --- | --- |

| 11 | Send scorecards to providers. Copy the medical director. Offer a 15-min 1-on-1 to any provider who wants to discuss. Output: Provider feedback delivered · 1-on-1s booked if requested. Notes: Providers respect specific, respectful feedback. Vague feedback earns pushback. |
| --- | --- |

Phase 3 · Establish rhythm  (days 22–45)

The first cycle proved it works. Now make it repeatable so you're not reinventing the process every month.

| 12 | Write a 1-page monthly SOP: 'Days 1-4 wait, 5-15 audit + HCC recapture (same pass), 15-20 scorecards, 20-25 queries and follow-up, 25-28 leadership summary.' Output: Written SOP saved in /Reference folder. Notes: Anchor it to the Audit Timing Calendar doc. |
| --- | --- |

| 13 | Do your second monthly audit cycle exactly the same way (audit + HCC in one pass). Time yourself. Adjust the SOP based on what actually worked vs. what didn't. Output: 60 total charts audited (30 baseline + 30 second cycle) · SOP v2 · HCC log now has two months of recapture data. Notes: By cycle 2 you'll know if 3 providers × 10 charts fits in your week or is too much. |
| --- | --- |

| 14 | Produce the first monthly leadership summary email — 5 bullets: charts audited, avg compliance %, providers in each band, HCCs recaptured + RAF impact, next-month focus. Output: First monthly summary sent to sponsor. Notes: Keep it under 200 words. Executives skim. |
| --- | --- |

| 15 | Build your first provider education tip (one page): pick the deficiency that showed up most across the 60 charts, write a 1-page 'before/after' example. Output: Provider Education Tip #1 published. Notes: Turn audit findings into teaching. This is where documentation actually improves. |
| --- | --- |

Phase 4 · Add HEDIS layer + expand  (days 46–75)

Documentation audits and HCC recapture are already running from day one. Now add the HEDIS/CPT II layer and, if bandwidth allows, expand the provider rotation. Cycle 3 is where the department starts looking like a full program instead of a pilot.

| 16 | Refresh the prior-year HCC lists for cycle 3 (patient panels evolve · pull the latest). Output: Updated HCC lists ready for cycle 3 audit + recapture pass. Notes: Same integrated workflow · audit + HCC together in one chart read. |
| --- | --- |

| 17 | Send provider queries for any suspect HCCs surfaced across cycles 1 and 2 that still need documentation. Track responses on the HCC Log. Output: Query log · provider responses tracked · recapture rate improves. Notes: Query template: neutral, specific, cite the chart evidence. |
| --- | --- |

| 18 | Add HEDIS / CPT II gap review to your monthly workflow — start with 3 measures (HbA1c control, BP control, BMI screening). Output: Gap list handed to the billing team · monthly HEDIS routine established. Notes: You are surfacing opportunities · the billing team codes them. |
| --- | --- |

| 19 | Decide whether to add a 4th or 5th provider to the audit rotation. If cycles 1-2 fit within your week comfortably, expand. Otherwise stay at 3. Output: Provider rotation confirmed for cycles 3-4. Notes: Grow the program only when the current load is sustainable. |
| --- | --- |

| 20 | Update the KPI Tracker Monthly Data tab with your first 3 months of data: providers on rotation, charts audited, avg compliance %, HCCs recaptured, HEDIS gaps closed, etc. Output: KPI Dashboard shows real numbers. Notes: This is what leadership will see in Phase 5. |
| --- | --- |

Phase 5 · First quarterly leadership report  (days 76–90)

Turn 90 days of work into a presentation that shows momentum, impact, and a specific ask.

| 21 | Open the Quarterly Report tab on the audit workbook. Confirm KPIs are populated. Review the Provider Progression chart. Output: Data-ready quarterly report. |
| --- | --- |

| 22 | Draft the Q1 leadership summary. Structure: 'What we built' · 'What we measured' · 'What we learned' · 'What we recommend next.' Keep it to 1 page + 3 supporting charts. Output: Q1 report draft. Notes: Use the KPI Tracker Dashboard and HCC Recapture Tracker Monthly Summary as source data. |
| --- | --- |

| 23 | Book the leadership presentation. Bring: the report, the audit workbook (live demo), the KPI Tracker, the HCC Recapture Tracker, the Audit Program Overview doc. Output: Meeting scheduled · presentation deck ready. Notes: A live demo lands harder than any slide. |
| --- | --- |

| 24 | Present. Ask for: continued executive sponsorship, formal recognition of the department, monthly 30-min check-in, and permission to draft the month-6 hire business case. Output: Signed approval on the four asks. Notes: Do NOT ask for the hire yet — that comes at month 6. Ask for permission to prepare it. |
| --- | --- |

| 25 | Publish everything to the shared drive: the report, the KPI dashboard PDF, the audit workbook, all 3 tool workbooks. Send a follow-up email to sponsor with links. Output: Documented paper trail leadership can reference later. Notes: Institutional memory · protects the program if you change roles. |
| --- | --- |

From Day 90 forward · monthly / quarterly rhythm

Once Phase 5 is complete, the department is officially launched. The recurring rhythm is now:

| Cadence | Activity |
| --- | --- |
| Every week | Audit 5–8 charts · review HCC list · draft queries · one provider follow-up. |
| Every month | 10 charts × 3-5 providers · scorecards · monthly leadership email · KPI Tracker update. |
| Every quarter | Full quarterly report · provider group education session · quarterly leadership presentation. |
| Every 6 months | Business case update · assess whether to request the CRC hire · policy review. |
| Annually | Full 12-month report · year-2 plan · budget cycle participation. |

Decision checkpoints along the way

| When | Decision | If yes then... | If no then... |
| --- | --- | --- | --- |
| End of Phase 2 | Did the first audit cycle finish in time? | Stay with 3 providers × 10 charts. | Reduce to 2 providers × 10 charts, revisit in Phase 4. |
| End of Phase 3 | Are providers engaging with feedback? | Add HCC review as planned. | Pause on adding new layers; work on provider relationships first. |
| End of Phase 4 | Are HCC recaptures producing measurable impact? | Include RAF impact prominently in Q1 report. | Focus Q1 report on documentation compliance improvements instead. |
| End of Phase 5 | Did leadership approve the four asks? | Follow the year-1 work plan as written. | Adjust scope · document the constraint · re-present at month 6. |

First 90 days · master checklist

Copy this into a task tracker or print it. Check each step as you complete it.

☐  Meet with executive sponsor · scope agreement signed

☐  Provider list confirmed · medical director endorsement

☐  Workspace set up · AutoSave on

☐  Payer portal access requested · prior-year HCC lists pulled

☐  Recurring calendar events booked

☐  10 charts × 3 providers pulled

☐  30 charts audited on Claim tabs · HCC recapture logged in the same pass

☐  3 provider scorecards sent (documentation + HCC feedback combined)

☐  1-on-1s booked if requested

☐  Monthly SOP written (audit + HCC as one integrated workflow)

☐  Cycle 2 completed (60 total charts audited · HCC log has 2 months of data)

☐  First monthly leadership summary sent

☐  Provider Education Tip #1 published

☐  Prior-year HCC lists refreshed for cycle 3

☐  Provider queries sent for suspect HCCs

☐  HEDIS / CPT II gap review started (3 measures)

☐  Decision made on expanding provider rotation (3 vs 4-5)

☐  KPI Tracker populated with 3 months of data

☐  Quarterly report drafted

☐  Leadership presentation delivered

☐  Four asks approved · month-6 hire prep permission granted

☐  All artifacts published to shared drive

End of startup workflow · come back to this doc anytime.